## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sakshi Saini | 2025-01-07 | Text extraction error in ocr | Sprit 1 | Sakshi Saini | User Interface | Pre-processing the images | 2025-01-08 | Closed | Pre-processing helps in it
2 | Sakshi Saini | 2025-01-27 | Uploading the app in stream cloud | Sprit 2 | Sakshi Saini | Standards | Add packages.txt in github | 2025-01-28 | Open | Needs further investigation

## Sheet2
Logical
User Interface
Maintainability
Standards
Others